## Slide 1
BANGKOK FLOOD FORECAST SYSTEM
Project Progress & Delivery Roadmap
ML-Powered Road Flood Forecasting, Live API Integration & Target Completion Schedule
Target Final Completion: August 24–28, 2026 | Current Status: Phase 10 (Live Pipeline Completed)

## Slide 2
BANGKOK FLOOD FORECAST V3.0
Executive Summary: Project Status & Target Readiness
Core ML & Replay Ready
53.3% Event POD
Trained LightGBM onset models achieve 53.3% event POD on 7 years of BMA historical data (2019-2025), accurately predicting road flooding 1-6h ahead.
Live Pipeline Deployed
Dual-Mode Serving
Built real-time data ingestion for ThaiWater, Open-Meteo GFS, and Traffy Fondue. Served side-by-side with Replay mode in backend API & dashboard.
Final Completion Window
August 24–28, 2026
On schedule for final model sign-off, high-resolution GFS downscaling, BMA live integration testing, and system handover.

## Slide 3
BANGKOK FLOOD FORECAST V3.0
Major Accomplishments Completed To Date
1. Data Ingestion & Quality | Phases 0 - 2
• Ingested 7 years (2019-2025) of BMA raw sensor data.
• Covering 131 rain gauges, 300 canal sensors, 107 road sensors.
• Engineered quality scorecards & defined 837 true flood events.
2. Spatial & External Modeling | Phases 3 - 4
• Processed 1m DTM elevation, depression depth & TWI.
• Integrated Open-Meteo GFS forecast rain (13km grid) & ERA5.
• Engineered 50 model-ready features with strict zero-leakage.
3. LightGBM ML & Calibration | Phases 5 & 8
• Trained LightGBM onset specialists across 1, 3, 6h horizons.
• Achieved 53.3% Event POD on test year 2025 (Replay mode).
• Calibrated probabilities & enforced strict CAP alert rules.
4. Live Dual-Mode Architecture | Phase 10 (Recent)
• Built src/bkkflood/live.py feature assembly pipeline.
• Integrated live ThaiWater, GFS forecast & Traffy Fondue feeds.
• Deployed live/replay mode toggle in API & React UI.

## Slide 4
BANGKOK FLOOD FORECAST V3.0
Live Forecast Capabilities & Input Requirements
Measured Performance Comparison
• Historical Replay Mode: 53.3% Event POD Uses 7-year archive of BMA 131 rain gauges & road sensors. • Current Public Live Mode: 4.9% Event POD Uses public ThaiWater canal + Open-Meteo GFS 13km rain grid. • Key Experimental Insight: Road sensors are NOT essential (removing them yields 45.1% POD). The single irreplaceable gap is BMA's 131 Live Rain Gauges.
Action Plan for Live Precision Boost
1. Request Live BMA Rain Gauge Feed Direct access to BMA's 131 rain gauges (5-min cadence) will instantly boost live detection from 5% to ~45% POD. 2. GFS Spatial Downscaling (1-km Grid) Downscale GFS 13-28km global grid to 1-km resolution to capture localized 2-5km Bangkok convective storm cells. 3. Live Sensor Coordinates Map exact GPS positions for 300 canal sensors to enable local district-level spatial joins.

## Slide 5
BANGKOK FLOOD FORECAST V3.0
Target Completion Timeline: August 24–28, 2026
Phase A: Aug 12–15
GFS Downscaling & API Request
• Build GFS 1-km spatial downscaling prototype.
• Submit formal request for BMA live rain gauge feed.
• Test high-res rainfall input ingestion.
Phase B: Aug 16–19
Sequence Model & DB Schema
• Integrate Phase 6 LSTM sequence model baseline.
• Finalize PostgreSQL / PostGIS database schema.
• Perform full backend load & stress testing.
Phase C: Aug 20–23
Sandbox & Integration Testing
• End-to-end sandbox testing with live collectors.
• Verify CAP 1.2 alert generation reliability.
• User acceptance testing & UI dashboard refinement.
Phase D: Aug 24–28
Final Sign-off & Delivery
• Final model validation & accuracy audit.
• Full documentation & handover package.
• Production deployment & official release.